## Start Here
SHRISH Complete QA Test Plan
Reusable release guide for development validation, production readiness, and post-deploy smoke testing
Workbook version | 1.0
Prepared for | SHRISH business website
Development URL | https://dev.shrish.co/
Production URL | https://www.shrish.co/
Generated | 2026-07-16
Test library | 190 detailed test cases
How to use this workbook
1 | Prepare | Use a dedicated test account, test email, Stripe test mode, and orders prefixed with QA.
2 | Run release gates | Complete the Release Checklist first. Stop if any P0 gate fails.
3 | Execute cases | Filter Test Cases by area, priority, environment, or device. Record Pass/Fail and evidence.
4 | Cover devices | Use Device Matrix to confirm desktop, iPhone, Android, and tablet coverage.
5 | Log defects | Create a Defect Log row for each failure and link its test case ID.
6 | Release decision | Approve only when all P0/P1 tests pass or have an explicitly accepted exception.
Release rules
Gate | All P0 and P1 cases Pass, or an owner documents and accepts the exception.
Defects | Zero open Critical or High defects. Medium defects require an owner and target date.
Payments | Use Stripe test mode on development. Never place an unapproved live production charge.
Production | Do deep testing on development. Production receives a controlled smoke test after deployment.
Data | Use test customers/orders and clean them up. Do not alter real customer orders for QA.
Evidence | Attach screenshot, order number, deployment URL, console log, or defect ID for every failure.
Status legend
Not Run | Pass | Fail | Blocked | N/A
Not executed | Matches expected result | Unexpected behavior | Cannot run due to dependency | Not applicable to this release

## Test Cases
Detailed Test Cases
Filter by priority, area, environment, or device. Enter execution results in the white columns.
Test ID | Area | Feature | Priority | Environment | Device / View | Preconditions | Test Steps | Expected Result | Status | Actual Result | Severity if Failed | Evidence / URL | Tester | Test Date | Defect / Notes
REL-001 | Release & deployment | Main/development branch alignment | P0 | Development | Git | Latest remote branches fetched | Compare main and developement commit history; document intentional differences. | No unexpected divergence; production changes are understood. | Not Run |  | N/A
REL-002 | Release & deployment | Clean working tree | P0 | Development | Git | Correct release branch checked out | Run git status and review every tracked/untracked file. | Only intended release files are present; no secrets, temp files, or accidental outputs. | Not Run |  | N/A
REL-003 | Release & deployment | Production branch mapping | P0 | Development | Vercel | Vercel access | Confirm Production tracks main and Preview/dev.shrish.co tracks developement. | Production cannot deploy from an unintended branch. | Not Run |  | N/A
REL-004 | Release & deployment | Preview deployment health | P0 | Development | Desktop | Latest preview deployed | Open dev.shrish.co and inspect deployment status and browser console. | Preview is Ready, correct commit is served, no boot errors. | Not Run |  | N/A
REL-005 | Release & deployment | Firebase Functions runtime | P0 | Development | CLI | Repository available | Confirm functions/package.json uses supported Node runtime and dependencies install cleanly. | Functions use Node 22 (or current approved runtime) and build successfully. | Not Run |  | N/A
REL-006 | Release & deployment | Functions and rules deployment | P0 | Development | Firebase | Firebase project selected | Verify intended Cloud Functions and Firestore rules are deployed to the correct project. | Deployed versions match the release commit. | Not Run |  | N/A
REL-007 | Release & deployment | Required environment variables | P0 | Development | Vercel/Firebase | Dashboard access | Check required Stripe, Resend, Maps, PostHog, URLs, tax, and shipping variables without exposing values. | Every required variable exists in the intended environment and no secret is client-exposed. | Not Run |  | N/A
REL-008 | Release & deployment | Stripe webhook registration | P0 | Development | Stripe | Stripe dashboard access | Verify webhook endpoint, selected events, signing secret, and recent successful deliveries. | Webhook deliveries return 2xx and use the correct environment secret. | Not Run |  | N/A
REL-009 | Release & deployment | Stripe enable flag decision | P0 | Development | Config | Release decision documented | Confirm STRIPE_PAYMENTS_ENABLED and test/live key modes match release intent. | No accidental live charging in dev; production behavior matches approved release. | Not Run |  | N/A
REL-010 | Release & deployment | Rollback point | P1 | Development | Git/Vercel | Candidate identified | Record the last known-good commit and Vercel deployment before release. | Rollback can be completed quickly without guessing. | Not Run |  | N/A
REL-011 | Release & deployment | Static asset cache refresh | P1 | Development + production smoke | Desktop + mobile | New deployment available | Hard reload; inspect CSS/JS/image responses and service-worker version. | New assets are served; old cached behavior does not persist. | Not Run |  | N/A
REL-012 | Release & deployment | Post-deploy smoke | P0 | Production | Desktop + mobile | Production deployment complete | Open home, shop, checkout, account, legal pages; add one item without completing live payment. | Critical production paths load and behave normally. | Not Run |  | N/A
NAV-001 | Public pages & navigation | All public pages load | P0 | Development + production smoke | Desktop + mobile | Site reachable | Open Home, About, Shop, Recipes, Contact, Account, Privacy, Refund, Terms. | Each page returns content, has no blank state, and shows the shared header/footer. | Not Run |  | N/A
NAV-002 | Public pages & navigation | Desktop header alignment | P1 | Development + production smoke | Desktop 1366/1440/1920 | Page loaded | Review logo, nav links, search, account, logout, and cart across widths. | Header remains aligned with no clipping or unintended wrapping. | Not Run |  | N/A
NAV-003 | Public pages & navigation | Mobile header alignment | P0 | Development + production smoke | iPhone + Android | Page loaded | Review logo, cart, and hamburger at 360, 375, 390, 412, and 430px. | Controls are evenly aligned and do not overlap content. | Not Run |  | N/A
NAV-004 | Public pages & navigation | Hamburger open and close | P0 | Development + production smoke | Mobile | Mobile viewport | Open menu, use close/hamburger, tap outside, press Escape where available. | Menu opens once, closes reliably, and restores page scrolling. | Not Run |  | N/A
NAV-005 | Public pages & navigation | Mobile menu content | P1 | Development + production smoke | Mobile | Menu open | Check Home, About, Shop, Recipes, Contact, Cart, Search, Order Now, Account/Logout. | Items are readable, tappable, correctly ordered, and route correctly. | Not Run |  | N/A
NAV-006 | Public pages & navigation | Search from header | P1 | Development + production smoke | Desktop + mobile | Products available | Search a full product name, partial name, and no-match term. | Relevant shop results appear; no-match state is helpful and reversible. | Not Run |  | N/A
NAV-007 | Public pages & navigation | Cart count consistency | P0 | Development + production smoke | Desktop + mobile | Cart starts empty | Add, increment, decrement, remove products; navigate between pages. | Header and floating cart counts always equal cart quantity. | Not Run |  | N/A
NAV-008 | Public pages & navigation | Announcement bar | P2 | Development + production smoke | Desktop + mobile | Page loaded | Review shipping/mango message for wrapping, accuracy, and link behavior. | Message is readable, current, and does not push or cover the header. | Not Run |  | N/A
NAV-009 | Public pages & navigation | Footer links | P1 | Development + production smoke | Desktop + mobile | Page loaded | Open all legal, contact, WhatsApp, Instagram, and policy links. | Links are correct, safe, and do not produce 404s. | Not Run |  | N/A
NAV-010 | Public pages & navigation | Back/forward browser navigation | P1 | Development + production smoke | Desktop + mobile | Navigate across three pages | Use browser back/forward repeatedly after filters and modal use. | Expected page state is restored without stale overlays or errors. | Not Run |  | N/A
HOM-001 | Homepage | First hero slide | P1 | Development + production smoke | Desktop + mobile | Fresh session | Open homepage and observe first slide. | Pickles are the entrance slide with matching image, copy, and CTA. | Not Run |  | N/A
HOM-002 | Homepage | Hero slide order | P1 | Development + production smoke | Desktop + mobile | Homepage open | Observe a full cycle. | Slides progress Pickles, Podi, Mangoes, Tathi Thandra in approved order. | Not Run |  | N/A
HOM-003 | Homepage | Hero timing | P2 | Development + production smoke | Desktop + mobile | Homepage open | Time two automatic transitions. | Each slide remains visible about 6 seconds and is readable. | Not Run |  | N/A
HOM-004 | Homepage | Hero content synchronization | P0 | Development + production smoke | Desktop + mobile | Homepage open | Observe every slide image, eyebrow, heading, body, and buttons. | Image and text always describe the same product group. | Not Run |  | N/A
HOM-005 | Homepage | Hero previous/next controls | P1 | Development + production smoke | Desktop + mobile | Homepage open | Click/tap previous and next several times. | Controls move exactly one slide and wrap correctly. | Not Run |  | N/A
HOM-006 | Homepage | Hero dots | P2 | Development + production smoke | Desktop + mobile | Homepage open | Select each dot and observe active state. | Correct slide opens and active indicator updates. | Not Run |  | N/A
HOM-007 | Homepage | Hero pause during interaction | P2 | Development + production smoke | Desktop + mobile | Homepage open | Hover/focus or interact with slide controls and CTA. | Autoplay does not steal the slide while customer is interacting. | Not Run |  | N/A
HOM-008 | Homepage | Hero category CTAs | P0 | Development + production smoke | Desktop + mobile | Homepage open | Click each Order/Shop CTA. | Shop opens with the intended Pickle, Podi, Mango, or Tathi Thandra context. | Not Run |  | N/A
HOM-009 | Homepage | Hero responsive framing | P1 | Development + production smoke | Mobile + tablet + desktop | Homepage open | Review images and text at standard viewport sizes. | Product remains inspectable; headline/buttons fit; next content is hinted without overlap. | Not Run |  | N/A
HOM-010 | Homepage | Chat/cart overlay spacing | P1 | Development + production smoke | Desktop + mobile | Widgets visible | Open chat and scroll through hero and first section. | Chat and cart controls never cover hero CTAs, arrows, or important text. | Not Run |  | N/A
SHP-001 | Shop & catalog | Category hierarchy | P0 | Development + production smoke | Desktop + mobile | Catalog loaded | Review filters for All Products, Sweets, Pickles, Podi, Snacks, Mangoes and veg/non-veg subfilters where applicable. | Categories are logically grouped, aligned, and easy to scan. | Not Run |  | N/A
SHP-002 | Shop & catalog | Category counts | P1 | Development + production smoke | Desktop + mobile | Catalog loaded | Compare displayed counts with visible products after each filter. | Counts equal the number of matching catalog products. | Not Run |  | N/A
SHP-003 | Shop & catalog | All Products filter | P0 | Development + production smoke | Desktop + mobile | Catalog loaded | Select All Products after using another filter. | All eligible products return and active state updates. | Not Run |  | N/A
SHP-004 | Shop & catalog | Sweets filter | P1 | Development + production smoke | Desktop + mobile | Catalog loaded | Select Sweets and any available subfilters. | Only sweets display; unrelated products are excluded. | Not Run |  | N/A
SHP-005 | Shop & catalog | Veg pickles filter | P1 | Development + production smoke | Desktop + mobile | Catalog loaded | Select Pickles then Veg. | Only vegetarian pickles display. | Not Run |  | N/A
SHP-006 | Shop & catalog | Non-veg pickles filter | P1 | Development + production smoke | Desktop + mobile | Catalog loaded | Select Pickles then Non-Veg. | Only non-vegetarian pickles display with preorder messaging where applicable. | Not Run |  | N/A
SHP-007 | Shop & catalog | Podi filter | P1 | Development + production smoke | Desktop + mobile | Catalog loaded | Select Podi. | Only podi/powder products display. | Not Run |  | N/A
SHP-008 | Shop & catalog | Snacks filter | P1 | Development + production smoke | Desktop + mobile | Catalog loaded | Select Snacks. | Only snacks display and zero-state is accurate if none are live. | Not Run |  | N/A
SHP-009 | Shop & catalog | Mangoes filter | P0 | Development + production smoke | Desktop + mobile | Catalog loaded | Select Fruits/Mangoes. | Only mango products display with correct availability. | Not Run |  | N/A
SHP-010 | Shop & catalog | Filter mouse-wheel behavior | P1 | Development + production smoke | Desktop | Long product list | Place pointer over category sidebar and use mouse wheel. | The page scrolls normally; the sidebar does not trap scrolling. | Not Run |  | N/A
SHP-011 | Shop & catalog | Price filter | P2 | Development + production smoke | Desktop + mobile | Catalog loaded | Set minimum/maximum boundaries and clear them. | Only products in range display and clearing restores results. | Not Run |  | N/A
SHP-012 | Shop & catalog | Sort options | P2 | Development + production smoke | Desktop + mobile | Catalog loaded | Test Featured, price low/high, and name sorting if available. | Ordering is correct and active filters remain applied. | Not Run |  | N/A
SHP-013 | Shop & catalog | Catalog search | P0 | Development + production smoke | Desktop + mobile | Catalog loaded | Search English and alternate product names such as podi/powder or prawn/shrimp. | Expected products are discoverable and result count is correct. | Not Run |  | N/A
SHP-014 | Shop & catalog | Dense product grid | P1 | Development + production smoke | Desktop | Catalog loaded | Review card density at 1366, 1440, and 1920 widths. | Cards are about 30% more compact while text, prices, and buttons remain readable. | Not Run |  | N/A
SHP-015 | Shop & catalog | Mobile product cards | P0 | Development + production smoke | Mobile | Catalog loaded | Scroll several card types, including long names and multiple variants. | No text/button overlap, horizontal scroll, or clipped price. | Not Run |  | N/A
SHP-016 | Shop & catalog | Availability badges | P0 | Development + production smoke | Desktop + mobile | Live and unavailable products exist | Inspect Available, Preorder, Coming Soon, and unavailable states. | Badge, button, and actual purchasability agree. | Not Run |  | N/A
SHP-017 | Shop & catalog | Notify when available | P1 | Development | Desktop + mobile | Unavailable product | Request notification with valid and invalid email; repeat request. | Valid request is saved once; duplicate and invalid submissions are handled clearly. | Not Run |  | N/A
SHP-018 | Shop & catalog | Product modal | P0 | Development + production smoke | Desktop + mobile | Catalog loaded | Open Details on products across categories. | Correct modal opens with title, description, pricing, variants, ingredients, policies, and close controls. | Not Run |  | N/A
SHP-019 | Shop & catalog | Product gallery | P0 | Development + production smoke | Desktop + mobile | Product with multiple images | Open modal, click each thumbnail, use keyboard/touch controls. | Every expected image loads, switches correctly, and stays within the frame. | Not Run |  | N/A
SHP-020 | Shop & catalog | Logo fallback | P1 | Development + production smoke | Desktop + mobile | Product without original photo | Open card/modal for a product with no approved photo. | SHRISH logo is used; no AI/stock/old mismatched image appears. | Not Run |  | N/A
SHP-021 | Shop & catalog | Variant add to cart | P0 | Development + production smoke | Desktop + mobile | Multi-size product | Add each size/price option and inspect cart. | Correct variant, unit price, name, and quantity are stored. | Not Run |  | N/A
SHP-022 | Shop & catalog | Card add to cart | P0 | Development + production smoke | Desktop + mobile | Available product | Add from card, add again, then open cart. | Cart updates once per click and merges/increments the matching variant correctly. | Not Run |  | N/A
SHP-023 | Shop & catalog | Unavailable product blocked | P0 | Development + production smoke | Desktop + mobile | Unavailable product | Try all purchase entry points. | Product cannot be added; Notify action is offered instead. | Not Run |  | N/A
SHP-024 | Shop & catalog | Admin catalog changes surface | P0 | Development | Desktop + mobile | Admin edit saved | Hard reload shop and find the edited item. | Approved price/content/image/availability changes are reflected without unrelated changes. | Not Run |  | N/A
CRT-001 | Cart & checkout UI | Cart persistence | P0 | Development + production smoke | Desktop + mobile | Cart contains items | Reload and navigate away/back. | Cart contents, variants, and quantities persist correctly. | Not Run |  | N/A
CRT-002 | Cart & checkout UI | Quantity increase | P0 | Development + production smoke | Desktop + mobile | Item in cart | Press plus repeatedly. | Quantity and totals update exactly once per tap/click. | Not Run |  | N/A
CRT-003 | Cart & checkout UI | Quantity decrease above one | P0 | Development + production smoke | Desktop + mobile | Quantity greater than one | Press minus. | Quantity decreases by one and totals recalculate. | Not Run |  | N/A
CRT-004 | Cart & checkout UI | Minus at quantity one | P0 | Development + production smoke | Desktop + mobile | Quantity equals one | Press minus. | Centered SHRISH-themed confirmation asks whether to remove the item. | Not Run |  | N/A
CRT-005 | Cart & checkout UI | Remove confirmation cancel | P1 | Development + production smoke | Desktop + mobile | Removal dialog open | Choose Cancel and press Escape where supported. | Dialog closes and item remains unchanged. | Not Run |  | N/A
CRT-006 | Cart & checkout UI | Remove confirmation approve | P0 | Development + production smoke | Desktop + mobile | Removal dialog open | Confirm removal. | Only the selected line is removed and totals/counts update. | Not Run |  | N/A
CRT-007 | Cart & checkout UI | Delete icon visibility | P1 | Development + production smoke | Desktop + mobile | Item in cart | Inspect delete control on desktop and mobile. | Boxed trash icon is visible, labeled for accessibility, and does not overlap price/quantity. | Not Run |  | N/A
CRT-008 | Cart & checkout UI | Delete icon behavior | P0 | Development + production smoke | Desktop + mobile | Item in cart | Activate trash icon, cancel once, confirm once. | The same themed confirmation is used and the correct item is removed. | Not Run |  | N/A
CRT-009 | Cart & checkout UI | Empty cart | P1 | Development + production smoke | Desktop + mobile | Remove final item | Observe empty state and CTA. | No stale totals remain; customer can return to shop. | Not Run |  | N/A
CRT-010 | Cart & checkout UI | Checkout totals presentation | P0 | Development + production smoke | Desktop + mobile | Cart contains items | Compare line totals, subtotal, tax, shipping, discount, and grand total. | Math is correct to cents and labels are unambiguous. | Not Run |  | N/A
CRT-011 | Cart & checkout UI | Mobile checkout layout | P0 | Development + production smoke | iPhone + Android | Cart contains long-name product | Review order card, quantity, price, delete, forms, and sticky CTA while scrolling. | No overlaps, clipped fields, hidden actions, or horizontal scrolling. | Not Run |  | N/A
CRT-012 | Cart & checkout UI | Sticky mobile CTA | P1 | Development + production smoke | Mobile | Checkout open | Scroll from top to bottom and open/close menu/dialog. | CTA stays usable without covering required fields, dialogs, or browser safe area. | Not Run |  | N/A
CRT-013 | Cart & checkout UI | Contact required fields | P0 | Development + production smoke | Desktop + mobile | Checkout open | Submit blank name, phone, and email; then correct each field. | Inline errors identify missing/invalid data and clear when corrected. | Not Run |  | N/A
CRT-014 | Cart & checkout UI | Phone validation | P1 | Development + production smoke | Desktop + mobile | Checkout open | Try short, formatted US, and international-style values. | Accepted formats are intentional; impossible values are blocked. | Not Run |  | N/A
CRT-015 | Cart & checkout UI | Email validation | P1 | Development + production smoke | Desktop + mobile | Checkout open | Try malformed and valid emails. | Malformed email is blocked; valid email is accepted. | Not Run |  | N/A
CRT-016 | Cart & checkout UI | Special instructions | P2 | Development + production smoke | Desktop + mobile | Checkout open | Enter punctuation and a long but reasonable note. | Text is retained, safely displayed, and stored with order. | Not Run |  | N/A
CRT-017 | Cart & checkout UI | Duplicate submit protection | P0 | Development | Desktop + mobile | Form complete | Double-click/tap submit and simulate slow response. | One order/payment session is created and button shows progress. | Not Run |  | N/A
PAY-001 | Payment, tax & fulfillment | Mango-only payment rule | P0 | Development | Desktop + mobile | Cart contains only mango | Open checkout and inspect fulfillment/payment options. | Pay at pickup is available; shipping and Stripe-only requirement are not shown. | Not Run |  | N/A
PAY-002 | Payment, tax & fulfillment | Mixed-cart payment rule | P0 | Development | Desktop + mobile | Cart contains mango plus non-mango | Open checkout. | Pay at pickup is available and shipping is unavailable for the mixed cart. | Not Run |  | N/A
PAY-003 | Payment, tax & fulfillment | Non-mango payment rule | P0 | Development | Desktop + mobile | Cart contains only pickle/podi/sweet/snack | Open checkout. | Online Stripe payment is required; Pay at pickup is not offered. | Not Run |  | N/A
PAY-004 | Payment, tax & fulfillment | Rule recalculation after mango removal | P0 | Development | Desktop + mobile | Mixed cart open | Remove all mango items without reloading. | Checkout immediately switches to non-mango online-payment rules. | Not Run |  | N/A
PAY-005 | Payment, tax & fulfillment | Rule recalculation after mango add | P0 | Development | Desktop + mobile | Non-mango cart open | Return to shop, add mango, reopen checkout. | Checkout follows mixed-cart pickup rule consistently. | Not Run |  | N/A
PAY-006 | Payment, tax & fulfillment | Pickup locations for pickup | P1 | Development | Desktop + mobile | Pickup-eligible cart | Choose pickup and review locations. | Approved pickup locations display and one is required. | Not Run |  | N/A
PAY-007 | Payment, tax & fulfillment | Pickup hidden for shipping | P0 | Development | Desktop + mobile | Shipping-eligible non-mango cart | Choose Shipping. | Pickup location cards and pickup-only instructions are hidden. | Not Run |  | N/A
PAY-008 | Payment, tax & fulfillment | Shipping address fields | P0 | Development | Desktop + mobile | Shipping selected | Review recipient, address line, city, state, ZIP, optional unit. | Required shipping fields are visible, labeled, and validate correctly. | Not Run |  | N/A
PAY-009 | Payment, tax & fulfillment | Address autocomplete | P0 | Development | Desktop + mobile | Google Places key/config active | Type a partial US street address slowly. | Relevant address suggestions appear without exposing the key beyond approved browser use. | Not Run |  | N/A
PAY-010 | Payment, tax & fulfillment | Select suggested address | P0 | Development | Desktop + mobile | Suggestions visible | Choose a suggestion. | Street, city, state, ZIP, and country populate accurately and remain editable. | Not Run |  | N/A
PAY-011 | Payment, tax & fulfillment | Manual address fallback | P1 | Development | Desktop + mobile | Autocomplete unavailable or no match | Enter a complete address manually. | Checkout remains usable and validates required fields. | Not Run |  | N/A
PAY-012 | Payment, tax & fulfillment | Address API failure | P1 | Development | Desktop + mobile | Simulate blocked/failed Places request | Type an address and inspect error handling. | No crash; customer sees a non-blocking fallback path. | Not Run |  | N/A
PAY-013 | Payment, tax & fulfillment | Virginia sales tax | P0 | Development | Desktop + mobile | Known cart amount | Calculate expected tax using configured rate and compare checkout/Stripe. | Displayed, saved, and charged tax match to the cent. | Not Run |  | N/A
PAY-014 | Payment, tax & fulfillment | Standard shipping fee | P0 | Development | Desktop + mobile | Eligible non-mango cart below threshold | Select shipping. | Configured standard shipping (currently $8.99 unless changed) is added once. | Not Run |  | N/A
PAY-015 | Payment, tax & fulfillment | Free shipping threshold | P0 | Development | Desktop + mobile | Eligible non-mango cart | Test $74.99, $75.00, and $75.01 merchandise totals. | Free shipping starts at the configured threshold with clear messaging. | Not Run |  | N/A
PAY-016 | Payment, tax & fulfillment | Mango shipping exclusion | P0 | Development | Desktop + mobile | Cart has mango | Attempt to reach shipping through UI and crafted state. | Shipping is blocked for mango-containing carts. | Not Run |  | N/A
PAY-017 | Payment, tax & fulfillment | Stripe test success | P0 | Development | Desktop + mobile | Stripe test mode | Complete checkout with Stripe success test card. | One successful payment, one order, paid status, and confirmation page result. | Not Run |  | N/A
PAY-018 | Payment, tax & fulfillment | Stripe decline | P0 | Development | Desktop + mobile | Stripe test mode | Use declined-card test data. | Clear recoverable error; no paid order and cart remains available. | Not Run |  | N/A
PAY-019 | Payment, tax & fulfillment | Stripe 3DS flow | P1 | Development | Desktop + mobile | Stripe test mode | Use authentication-required test card and complete/cancel challenge. | Both paths return safely with accurate order/payment state. | Not Run |  | N/A
PAY-020 | Payment, tax & fulfillment | Stripe cancel/back | P1 | Development | Desktop + mobile | Stripe checkout launched | Cancel and return to site. | Customer returns to the same environment with cart/order state intact. | Not Run |  | N/A
PAY-021 | Payment, tax & fulfillment | Development return host | P0 | Development | Desktop + mobile | Start at dev.shrish.co | Complete Stripe test payment. | Success/cancel returns to dev.shrish.co, never shrish.co. | Not Run |  | N/A
PAY-022 | Payment, tax & fulfillment | Confirmation order number | P1 | Development | Desktop + mobile | Successful order | Review confirmation page and account prompt. | Order number is prominent, gold, readable, and consistent everywhere. | Not Run |  | N/A
PAY-023 | Payment, tax & fulfillment | Webhook paid status | P0 | Development | Stripe/Firebase | Successful Stripe payment | Inspect webhook delivery and stored order after completion. | Webhook is verified and order becomes paid exactly once. | Not Run |  | N/A
PAY-024 | Payment, tax & fulfillment | Webhook idempotency | P0 | Development | Stripe/Firebase | Successful event exists | Replay the same Stripe event. | No duplicate order, email, inventory update, or accounting entry. | Not Run |  | N/A
PAY-025 | Payment, tax & fulfillment | Server price tamper defense | P0 | Development | DevTools/API | Test environment and known product price | Alter client/cart price before creating checkout session. | Server ignores/rejects tampered price and Stripe uses authoritative catalog price. | Not Run |  | N/A
PAY-026 | Payment, tax & fulfillment | Promo percent | P1 | Development | Desktop + mobile | Valid percent promo | Apply valid code, wrong case, then remove it. | Discount, tax, total, and usage rules calculate correctly. | Not Run |  | N/A
PAY-027 | Payment, tax & fulfillment | Promo fixed amount | P1 | Development | Desktop + mobile | Valid fixed promo | Apply below and above discount value. | Discount never makes merchandise total negative and totals remain accurate. | Not Run |  | N/A
PAY-028 | Payment, tax & fulfillment | Promo free shipping | P1 | Development | Desktop + mobile | Shipping-eligible cart and valid code | Apply code before and after choosing shipping. | Shipping becomes free only when eligibility requirements are met. | Not Run |  | N/A
PAY-029 | Payment, tax & fulfillment | Promo restrictions | P1 | Development | Desktop + mobile | Expired/minimum/one-use/capped promos | Test each restriction and repeat one-use code. | Invalid uses are rejected with specific, safe messages. | Not Run |  | N/A
ACC-001 | Customer accounts | Create account | P0 | Development | Desktop + mobile | Unused test email | Register with valid details and verify account state. | Account is created, signed in, and profile is available. | Not Run |  | N/A
ACC-002 | Customer accounts | Create account validation | P1 | Development | Desktop + mobile | Account page open | Try duplicate email, weak password, mismatch, and missing fields. | Specific errors display without exposing sensitive details. | Not Run |  | N/A
ACC-003 | Customer accounts | Sign in and sign out | P0 | Development | Desktop + mobile | Existing test account | Sign in, navigate, refresh, then sign out. | Session persists as intended and sign-out removes protected access. | Not Run |  | N/A
ACC-004 | Customer accounts | Password reset | P1 | Development | Desktop + mobile | Existing test email | Request reset and inspect email/confirmation. | One safe reset flow is sent and UI does not reveal unknown accounts. | Not Run |  | N/A
ACC-005 | Customer accounts | Edit profile | P1 | Development | Desktop + mobile | Signed in | Update name, phone, preferred pickup, city/address. | Changes save and prefill checkout without corrupting order history. | Not Run |  | N/A
ACC-006 | Customer accounts | Claim recent order | P1 | Development | Desktop + mobile | Guest order and matching account data | Create/sign in with matching email/phone. | Eligible order links once to the correct account. | Not Run |  | N/A
ACC-007 | Customer accounts | Purchase history | P0 | Development | Desktop + mobile | Account has orders | Open history and compare order cards to Firestore/admin. | Order number, date, items, total, payment, status, and location match. | Not Run |  | N/A
ACC-008 | Customer accounts | Order details modal | P1 | Development | Desktop + mobile | Order exists | Open and close details; review all values. | Correct order opens and modal is responsive/keyboard accessible. | Not Run |  | N/A
ACC-009 | Customer accounts | Edit pending quantity | P0 | Development | Desktop + mobile | Eligible pending order | Increase/decrease existing item and save. | Order totals and admin view update safely. | Not Run |  | N/A
ACC-010 | Customer accounts | Add item to pending order | P1 | Development | Desktop + mobile | Eligible pending order | Use available edit/shop path to add a new product if supported. | New item can be added only when business rules allow, with correct total/payment handling. | Not Run |  | N/A
ACC-011 | Customer accounts | Cancel pending order | P0 | Development | Desktop + mobile | Cancelable pending order | Cancel, confirm, refresh, inspect admin. | Order is canceled once and cannot be processed as active. | Not Run |  | N/A
ACC-012 | Customer accounts | Prevent ineligible edit/cancel | P0 | Development | Desktop + mobile | Paid/fulfilled/canceled order | Attempt edit/cancel through UI and crafted request. | Server and UI reject unauthorized state changes. | Not Run |  | N/A
ACC-013 | Customer accounts | Order again | P1 | Development | Desktop + mobile | Historical order | Choose Order Again and inspect cart. | Available items/variants are added; unavailable products are clearly handled. | Not Run |  | N/A
ACC-014 | Customer accounts | Feedback | P1 | Development | Desktop + mobile | Eligible fulfilled order | Submit rating and answers; repeat submission. | Feedback saves once and appears in admin with correct order/customer. | Not Run |  | N/A
ACC-015 | Customer accounts | Cross-account isolation | P0 | Development | Security | Two test accounts | Attempt to access another user's order/profile identifiers. | Unauthorized reads/writes are denied by UI and Firestore rules. | Not Run |  | N/A
NTF-001 | Notifications & communications | Product notification request | P1 | Development | Desktop + mobile | Unavailable product | Submit notify request and inspect admin/Firestore. | Request contains correct product and contact data once. | Not Run |  | N/A
NTF-002 | Notifications & communications | Availability email target | P0 | Development | Email | Two users subscribed to different products | Mark one product available through the approved admin action. | Only subscribers to that product receive the availability email. | Not Run |  | N/A
NTF-003 | Notifications & communications | No email on unrelated sync | P0 | Development | Email/Admin | Product subscriptions exist | Use price sync without changing availability. | No availability email is sent and no product is toggled live. | Not Run |  | N/A
NTF-004 | Notifications & communications | Email reminder | P1 | Development | Admin/Email | Pending order with valid email | Send reminder from active orders. | One correctly branded reminder references the right order/location. | Not Run |  | N/A
NTF-005 | Notifications & communications | WhatsApp reminder | P1 | Development | Desktop + mobile | Pending order with phone | Open WhatsApp reminder. | Correct number and prefilled, accurate order message are used. | Not Run |  | N/A
NTF-006 | Notifications & communications | Order confirmation email | P0 | Development | Email | Complete pickup and Stripe test orders | Inspect both emails. | Order number, items, totals, payment, and fulfillment details are accurate. | Not Run |  | N/A
NTF-007 | Notifications & communications | Email failure handling | P1 | Development | Functions | Simulate email provider error | Place order or send reminder. | Order remains valid; error is logged and admin/customer receives safe feedback. | Not Run |  | N/A
ADM-001 | Admin operations | Admin access control | P0 | Development | Desktop + mobile | Signed out/non-admin/admin accounts | Attempt admin URL and sign in with each account. | Only authorized admins can view or mutate admin data. | Not Run |  | N/A
ADM-002 | Admin operations | Admin navigation | P1 | Development | Desktop + tablet | Admin signed in | Open every sidebar section and return to Orders. | All sections render, active state is correct, no content is hidden by navigation. | Not Run |  | N/A
ADM-003 | Admin operations | Summary metrics | P1 | Development | Desktop | Admin data loaded | Reconcile total orders, pending, fulfilled, revenue, boxes, products live, subscribers. | Cards match source data and definitions. | Not Run |  | N/A
ADM-004 | Admin operations | Active orders | P0 | Development | Desktop | Pending orders exist | Search/filter by order, customer, location, date, and status. | Only matching active orders display and counts recalculate. | Not Run |  | N/A
ADM-005 | Admin operations | Active item counts | P1 | Development | Desktop | Active orders exist | Sum product quantities manually and compare chips. | Order, box, and item counts are accurate and readable. | Not Run |  | N/A
ADM-006 | Admin operations | Manual order | P0 | Development | Desktop | Admin signed in | Create a manual pickup order with multiple items. | One valid order appears in active/admin/account flows with correct totals. | Not Run |  | N/A
ADM-007 | Admin operations | Edit active order | P0 | Development | Desktop | Pending order | Edit customer/items/quantities where allowed and save. | Changes persist safely and totals/counts update. | Not Run |  | N/A
ADM-008 | Admin operations | Fulfill order | P0 | Development | Desktop | Pending order | Fulfill one order and inspect processed/all/accounting. | Order leaves active list and is fulfilled exactly once. | Not Run |  | N/A
ADM-009 | Admin operations | Bulk fulfill | P0 | Development | Desktop | Multiple filtered pending orders | Select a subset and use bulk fulfill. | Only selected/filtered eligible orders change state. | Not Run |  | N/A
ADM-010 | Admin operations | No show/cancel/reset | P1 | Development | Desktop | Test orders | Apply each action and confirm resulting lists/statuses. | Transitions follow allowed state rules and are reversible only where intended. | Not Run |  | N/A
ADM-011 | Admin operations | Processed and all orders | P1 | Development | Desktop | Orders in multiple states | Search/filter/export and open details. | All states display in the correct section with complete data. | Not Run |  | N/A
ADM-012 | Admin operations | Active Excel export | P1 | Development | Desktop | Filtered active list | Export and open workbook. | Rows/columns match filtered orders and values are usable. | Not Run |  | N/A
ADM-013 | Admin operations | Print checklist content | P0 | Development | Print preview | Active orders exist | Print checklist and inspect headers/rows. | Payment type checkboxes are present; How to Use and Revenue are absent; layout is legible. | Not Run |  | N/A
ADM-014 | Admin operations | Active columns | P1 | Development | Desktop | Active orders open | Inspect table and print output. | Unneeded Payment and Status columns remain removed where requested without losing actions. | Not Run |  | N/A
ADM-015 | Admin operations | Add product collapsed | P1 | Development | Desktop | Manage Products open | Confirm form is hidden; open Add New Product, complete, save, cancel. | Form appears only on request and saves/cancels predictably. | Not Run |  | N/A
ADM-016 | Admin operations | Product filters and compact cards | P1 | Development | Desktop | Manage Products open | Filter each category and scroll cards. | Filters align, product cards stay compact, controls remain readable. | Not Run |  | N/A
ADM-017 | Admin operations | Edit product | P0 | Development | Desktop | Test product | Change one safe field, save, reload admin and shop. | Only intended field changes and storefront reflects it. | Not Run |  | N/A
ADM-018 | Admin operations | Product availability toggle | P0 | Development | Desktop | Test product unavailable | Toggle live, save, reload shop; toggle off again. | Only target product changes availability and notify workflow runs only when appropriate. | Not Run |  | N/A
ADM-019 | Admin operations | Sync prices isolation | P0 | Development | Desktop | Mango products off and mixed catalog | Record availability; run Sync Prices to Live Store; reload admin/shop. | Prices sync as designed; availability flags, especially mangoes, do not change. | Not Run |  | N/A
ADM-020 | Admin operations | Product order/save | P1 | Development | Desktop | Manage Products open | Change display order and save. | Only intended product ordering changes in storefront. | Not Run |  | N/A
ADM-021 | Admin operations | Hide product | P1 | Development | Desktop | Test product | Hide/unhide and reload shop. | Hidden item is not purchasable/discoverable; unhide restores it. | Not Run |  | N/A
ADM-022 | Admin operations | Product image fields | P0 | Development | Desktop | Manage Products edit | Review primary/gallery path fields and save approved images. | Valid paths persist, render, and do not overwrite unrelated galleries. | Not Run |  | N/A
ADM-023 | Admin operations | Customer accounts admin | P1 | Development | Desktop | Accounts exist | Search/export; inspect orders; test permitted deletion. | Counts are accurate; only accounts with no orders can be deleted. | Not Run |  | N/A
ADM-024 | Admin operations | Feedback admin | P1 | Development | Desktop | Feedback exists | Filter/search by rating/location/product and inspect summary. | Summary and rows match submissions and remain readable. | Not Run |  | N/A
ADM-025 | Admin operations | Subscribers admin | P1 | Development | Desktop | Subscribers exist | Search/export/delete approved test subscriber. | Data is accurate and deletion targets only selected record. | Not Run |  | N/A
ADM-026 | Admin operations | Promo codes admin | P0 | Development | Desktop | Admin signed in | Create/edit/disable percent, fixed, free shipping, minimum, cap, expiry, one-use codes. | Rules persist and checkout enforces exactly what admin configured. | Not Run |  | N/A
ADM-027 | Admin operations | Refund controls | P0 | Development | Desktop | Paid Stripe test order | Inspect refund eligibility and test-mode refund flow. | Customer refund UI remains hidden; admin refund is deliberate, auditable, and updates status. | Not Run |  | N/A
ADM-028 | Admin operations | Accounting batch dropdown | P1 | Development | Desktop | Open/closed batches exist | Use dropdowns to select open/closed batches and open breakdown. | No long uncontrolled scroll; selected batch metrics are compact and correct. | Not Run |  | N/A
ADM-029 | Admin operations | Accounting save/close/reopen | P0 | Development | Desktop | Test batch | Save tally, close, locate closed, reopen, verify totals. | State and totals persist without duplicate batches. | Not Run |  | N/A
ADM-030 | Admin operations | Accounting export | P1 | Development | Desktop | Batch selected | Export CSV and reconcile key fields. | Export matches displayed batch and is usable for bookkeeping. | Not Run |  | N/A
ADM-031 | Admin operations | Pickup tally compact layout | P1 | Development | Desktop + tablet | Tally open | Review invoice, cash, Zelle, card, and balance inputs. | Panels are compact, aligned, and all numeric calculations are accurate. | Not Run |  | N/A
ADM-032 | Admin operations | Growth analytics | P2 | Development | Desktop | Analytics data available | Open Growth Dashboard and compare key events/metrics with source. | Charts/metrics load without exposing PII and definitions are clear. | Not Run |  | N/A
SEO-001 | SEO & content | Unique page titles | P1 | Development + production smoke | Desktop | Pages reachable | Inspect title for every indexable page. | Each title is unique, descriptive, and includes SHRISH appropriately. | Not Run |  | N/A
SEO-002 | SEO & content | Meta descriptions | P1 | Development + production smoke | Desktop | Pages reachable | Inspect description tags for indexable pages. | Descriptions are unique, accurate, and compelling without keyword stuffing. | Not Run |  | N/A
SEO-003 | SEO & content | Self-referencing canonicals | P0 | Production | Production pages reachable | Inspect canonical on Home, Shop, About, Contact, Recipes, Privacy, Refund, Terms. | Each points to its preferred www.shrish.co URL; no duplicate/missing canonical. |  | Not Run |  | N/A
SEO-004 | SEO & content | Robots directives | P0 | Development + production smoke | Desktop | Pages reachable | Inspect robots meta and robots.txt. | Public content is indexable; order, account, admin, and development are protected from indexing. | Not Run |  | N/A
SEO-005 | SEO & content | Sitemap | P1 | Production | sitemap.xml reachable | Open sitemap and verify listed URLs, protocol, host, and current public pages. | Only canonical public URLs are listed and all return 200. |  | Not Run |  | N/A
SEO-006 | SEO & content | Structured data | P1 | Production | Public pages reachable | Run Google rich result/schema validation on organization and product data. | Valid schema uses accurate business/product information and prices/availability. |  | Not Run |  | N/A
SEO-007 | SEO & content | Open Graph/social metadata | P2 | Production | Public pages reachable | Inspect og:title, description, URL, image and share preview. | Share preview is branded, readable, and uses an approved image. |  | Not Run |  | N/A
SEO-008 | SEO & content | Heading structure | P1 | Development + production smoke | Desktop + mobile | Pages reachable | Inspect H1-H3 hierarchy and visible page names. | One meaningful H1 per page and logical nested headings. | Not Run |  | N/A
SEO-009 | SEO & content | Image alt text | P1 | Development + production smoke | Desktop + mobile | Images loaded | Inspect product, hero, recipe, and logo alt text. | Alt text identifies meaningful images; decorative images are appropriately ignored. | Not Run |  | N/A
SEO-010 | SEO & content | Broken links/assets | P0 | Development + production smoke | Crawler + browser | Site reachable | Crawl internal links and inspect network 404/500 responses. | No broken internal links, missing scripts/styles, or missing product images. | Not Run |  | N/A
SEO-011 | SEO & content | Legal content links | P0 | Development + production smoke | Desktop + mobile | Checkout/footer open | Open Privacy, Refund, Terms from footer and checkout agreement. | Pages load, dates/contact/business terms are current, and links point to canonical pages. | Not Run |  | N/A
SEO-012 | SEO & content | Content accuracy | P1 | Development + production smoke | Desktop + mobile | Catalog and policies available | Proofread pricing, product names, weights, pickup/shipping/payment statements, allergy notices. | Copy matches actual business rules with no contradictory claims. | Not Run |  | N/A
A11Y-001 | Accessibility & responsive UI | Keyboard navigation | P1 | Development + production smoke | Desktop | Page loaded | Use Tab/Shift+Tab/Enter/Space through header, filters, cards, forms, dialogs. | Focus order is logical and all actions work without a mouse. | Not Run |  | N/A
A11Y-002 | Accessibility & responsive UI | Visible focus | P1 | Development + production smoke | Desktop + mobile | Keyboard navigation | Observe focus on links, buttons, fields, thumbnails, dialog controls. | Focus indicator is clearly visible against dark and light backgrounds. | Not Run |  | N/A
A11Y-003 | Accessibility & responsive UI | Modal focus management | P1 | Development + production smoke | Desktop | Open product/remove/order modal | Tab through, press Escape, check focus after close. | Focus is trapped inside while open and returns to the trigger. | Not Run |  | N/A
A11Y-004 | Accessibility & responsive UI | Form labels and errors | P0 | Development + production smoke | Desktop + mobile | Forms available | Inspect accessible names; trigger validation errors with screen reader or accessibility tree. | Every field has a persistent label and errors are programmatically associated. | Not Run |  | N/A
A11Y-005 | Accessibility & responsive UI | Color contrast | P1 | Development + production smoke | Desktop + mobile | Pages loaded | Check gold, muted text, badges, buttons, form placeholders on black/cream surfaces. | Essential text and controls meet WCAG AA contrast. | Not Run |  | N/A
A11Y-006 | Accessibility & responsive UI | Zoom 200 percent | P1 | Development + production smoke | Desktop | Browser at 200% | Navigate home, shop, checkout, account, legal pages. | Content reflows without loss, overlap, or horizontal scrolling. | Not Run |  | N/A
A11Y-007 | Accessibility & responsive UI | Text size and long content | P1 | Development + production smoke | Mobile | Largest system text/long product names | Review navigation, cards, checkout, admin tables where applicable. | Text wraps cleanly and controls retain stable dimensions. | Not Run |  | N/A
A11Y-008 | Accessibility & responsive UI | Touch targets | P1 | Development + production smoke | Mobile | Mobile viewport | Measure/tap hamburger, cart, arrows, plus/minus, trash, thumbnails, filters. | Targets are comfortably tappable and separated. | Not Run |  | N/A
A11Y-009 | Accessibility & responsive UI | Safe-area handling | P1 | Development + production smoke | iPhone Safari | Notched iPhone | Review header, fixed CTA, floating widgets, and bottom browser chrome. | No action is hidden under notches, home indicator, or browser controls. | Not Run |  | N/A
A11Y-010 | Accessibility & responsive UI | Reduced motion | P2 | Development + production smoke | Desktop + mobile | OS prefers-reduced-motion enabled | Open homepage and interactions. | Autoplay/animations are reduced or non-disruptive. | Not Run |  | N/A
A11Y-011 | Accessibility & responsive UI | No horizontal overflow | P0 | Development + production smoke | 360-430px mobile | Each page open | Swipe horizontally at top/middle/bottom. | Page has no unintended horizontal movement or clipped off-screen controls. | Not Run |  | N/A
A11Y-012 | Accessibility & responsive UI | Landscape mobile/tablet | P2 | Development + production smoke | Mobile landscape + tablet | Rotate device | Review header, modal, shop, and checkout. | Layout adapts without requiring reload and remains usable. | Not Run |  | N/A
PERF-001 | Performance, security & analytics | Console and network health | P0 | Development + production smoke | Desktop + mobile | DevTools open | Navigate all major flows and filter console/network errors. | No uncaught errors, repeated failures, mixed content, or unexplained 4xx/5xx. | Not Run |  | N/A
PERF-002 | Performance, security & analytics | Core Web Vitals | P1 | Production | Mobile + desktop | Run Lighthouse/PageSpeed on Home, Shop, Checkout. | LCP, CLS, and INP are within agreed thresholds or documented. |  | Not Run |  | N/A
PERF-003 | Performance, security & analytics | Image optimization | P1 | Development + production smoke | Desktop + mobile | Network throttling | Inspect dimensions, file sizes, lazy loading, and below-fold requests. | Images are appropriately sized/compressed; below-fold assets lazy load. | Not Run |  | N/A
PERF-004 | Performance, security & analytics | Service worker update | P0 | Development + production smoke | Desktop + mobile | Old version cached | Load old deployment, release new version, refresh/reopen. | Customer receives new JS/CSS/catalog without a broken mixed-version state. | Not Run |  | N/A
PERF-005 | Performance, security & analytics | Firestore unauthorized access | P0 | Development | Security | Signed-out/non-admin session | Attempt direct reads/writes to orders, admin data, refunds, promos, notifications. | Rules deny unauthorized operations while valid customer/admin flows still work. | Not Run |  | N/A
PERF-006 | Performance, security & analytics | API key restrictions | P0 | Development | Google Cloud | Maps key configured | Verify HTTP referrers and API restrictions for dev, shrish.co, www.shrish.co. | Key works only on approved hosts and only required Maps/Places APIs. | Not Run |  | N/A
PERF-007 | Performance, security & analytics | Secret scan | P0 | Development | Repository | Release candidate | Scan tracked files/history/diff for Stripe, webhook, Resend, Firebase admin, Maps, and other secrets. | No server secret or unrestricted sensitive credential is committed. | Not Run |  | N/A
PERF-008 | Performance, security & analytics | Analytics page views | P2 | Development + production smoke | Desktop + mobile | Analytics enabled | Navigate public pages and inspect analytics debugger/network. | One page-view event per navigation with correct path and no PII. | Not Run |  | N/A
PERF-009 | Performance, security & analytics | Commerce analytics | P2 | Development | Desktop + mobile | Analytics enabled | Search, view product, add/remove cart, begin checkout, purchase test order. | Expected events fire once with correct product/value metadata and no PII. | Not Run |  | N/A
PERF-010 | Performance, security & analytics | Error logging | P1 | Development | Functions/browser | Safe simulated error | Trigger recoverable client/function error and inspect logs. | Enough context is logged for diagnosis without storing secrets or payment data. | Not Run |  | N/A

## Release Dashboard
Release Dashboard
Formula-driven summary of the Test Cases sheet. Update statuses there and this page refreshes automatically.
Execution summary
Metric | Result |  |  |  |  | Status | Count
Total cases | 190 |  |  |  |  | Pass | 0
Executed | 0 |  |  |  |  | Fail | 0
Pass | 0 |  |  |  |  | Blocked | 0
Fail | 0 |  |  |  |  | Not Run | 190
Blocked | 0 |  |  |  |  | N/A | 0
Not Run | 190
Pass rate | 0%
Coverage by area
Area | Total | Pass | Fail | Blocked | Not Run
Release & deployment | 12 | 0 | 0 | 0 | 12
Public pages & navigation | 10 | 0 | 0 | 0 | 10
Homepage | 10 | 0 | 0 | 0 | 10
Shop & catalog | 24 | 0 | 0 | 0 | 24
Cart & checkout UI | 17 | 0 | 0 | 0 | 17
Payment, tax & fulfillment | 29 | 0 | 0 | 0 | 29
Customer accounts | 15 | 0 | 0 | 0 | 15
Notifications & communications | 7 | 0 | 0 | 0 | 7
Admin operations | 32 | 0 | 0 | 0 | 32
SEO & content | 12 | 0 | 0 | 0 | 12
Accessibility & responsive UI | 12 | 0 | 0 | 0 | 12
Performance, security & analytics | 10 | 0 | 0 | 0 | 10

## Device Matrix
Device & Browser Matrix
Use real devices where possible. Evidence should include screenshot, viewport, browser version, and test date.
ID | Platform | Device / Viewport | Browser | Required Scope | Priority | Status | Evidence | Tester | Date / Notes
DEV-01 | Windows 11 | 1366 x 768 | Chrome latest | Full public regression + admin | P0 | Not Run
DEV-02 | Windows 11 | 1920 x 1080 | Chrome latest | Visual density, shop, admin | P1 | Not Run
DEV-03 | Windows 11 | 1440 x 900 | Edge latest | Public smoke + checkout | P1 | Not Run
DEV-04 | macOS | 1440 x 900 or similar | Safari latest | Public smoke + checkout | P2 | Not Run
DEV-05 | iOS | iPhone SE / 375 x 667 | Safari | Header, shop, checkout, account | P0 | Not Run
DEV-06 | iOS | iPhone 14/15 / 390 x 844 | Safari | Full mobile regression | P0 | Not Run
DEV-07 | iOS | iPhone Pro Max / 430 x 932 | Safari | Large mobile + safe area | P1 | Not Run
DEV-08 | Android | 360 x 800 | Chrome | Small Android regression | P0 | Not Run
DEV-09 | Android | 412 x 915 | Chrome | Full mobile regression | P0 | Not Run
DEV-10 | iPad/tablet | 768 x 1024 portrait | Safari/Chrome | Responsive public + checkout | P1 | Not Run
DEV-11 | iPad/tablet | 1024 x 768 landscape | Safari/Chrome | Responsive public + admin | P2 | Not Run
DEV-12 | Accessibility | 200% zoom + keyboard | Chrome/Edge | Public + checkout + dialogs | P1 | Not Run

## Image Audit
Verified Product Image Audit
Confirms every approved original image appears under the correct product on card, modal gallery, desktop, and mobile.
Product | Expected image files | Expected count | Card image correct | Modal gallery count | Images match product | No old/mismatched image | Mobile crop | All files load | Status | Evidence / Notes
Cauliflower Pickle | cauliflower-pickle-verified-1.jpg cauliflower-pickle-verified-2.jpg cauliflower-pickle-verified-3.jpg | 3 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Drumstick Pickle | drumstick-pickle-verified-1.jpg drumstick-pickle-verified-2.jpg | 2 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Gongura Pickle / Pachadi | gongura-pickle-verified-1.jpg gongura-pickle-verified-2.jpg gongura-pickle-verified-3.jpg | 3 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Mixed Vegetable Pickle | mix-veg-pickle-original-1.jpg mix-veg-pickle-original-2.jpg mix-veg-pickle-original-3.jpg | 3 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Chicken Boneless Pickle | chicken-boneless-pickle-verified-1.jpg chicken-boneless-pickle-verified-2.jpg chicken-boneless-pickle-verified-3.jpg | 3 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Mutton Boneless | mutton-boneless-pickle-verified-1.jpg mutton-boneless-pickle-verified-2.jpg | 2 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Prawns / Shrimp Pickle | shrimp-pickle-verified-1.jpg shrimp-pickle-verified-2.jpg | 2 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Moringa Powder / Munagaku Podi | moringa-podi-verified-1.jpg moringa-podi-verified-2.jpg | 2 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Idli Podi | idli-podi-verified-1.jpg idli-podi-verified-2.jpg | 2 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Karivepaku Podi / Curry Leaf Powder | curry-leaf-podi-verified-1.jpg curry-leaf-podi-verified-2.jpg | 2 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Karela / Kakarakaya Pickle | karela-pickle-verified-1.jpg karela-pickle-verified-2.jpg | 2 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Flaxseed Podi | flaxseed-podi-verified-1.jpg flaxseed-podi-verified-2.jpg | 2 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run
Kakarakaya Karam / Bitter Gourd Podi | karela-podi-verified-1.jpg karela-podi-verified-2.jpg | 2 | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run | Not Run

## Defect Log
Defect Log
Create one row for every failed test. Keep reproduction steps exact and attach evidence.
Defect ID | Test Case ID | Title | Severity | Page / Feature | Environment | Device / Browser | Reproduction Steps | Actual Result | Expected Result | Evidence | Owner | Status | Opened | Closed / Retest Notes
BUG-001 |  |  | Medium |  | Development | [6 empty] | Open
BUG-002 |  |  | Medium |  | Development | [6 empty] | Open
BUG-003 |  |  | Medium |  | Development | [6 empty] | Open
BUG-004 |  |  | Medium |  | Development | [6 empty] | Open
BUG-005 |  |  | Medium |  | Development | [6 empty] | Open
BUG-006 |  |  | Medium |  | Development | [6 empty] | Open
BUG-007 |  |  | Medium |  | Development | [6 empty] | Open
BUG-008 |  |  | Medium |  | Development | [6 empty] | Open
BUG-009 |  |  | Medium |  | Development | [6 empty] | Open
BUG-010 |  |  | Medium |  | Development | [6 empty] | Open
BUG-011 |  |  | Medium |  | Development | [6 empty] | Open
BUG-012 |  |  | Medium |  | Development | [6 empty] | Open
BUG-013 |  |  | Medium |  | Development | [6 empty] | Open
BUG-014 |  |  | Medium |  | Development | [6 empty] | Open
BUG-015 |  |  | Medium |  | Development | [6 empty] | Open
BUG-016 |  |  | Medium |  | Development | [6 empty] | Open
BUG-017 |  |  | Medium |  | Development | [6 empty] | Open
BUG-018 |  |  | Medium |  | Development | [6 empty] | Open
BUG-019 |  |  | Medium |  | Development | [6 empty] | Open
BUG-020 |  |  | Medium |  | Development | [6 empty] | Open
BUG-021 |  |  | Medium |  | Development | [6 empty] | Open
BUG-022 |  |  | Medium |  | Development | [6 empty] | Open
BUG-023 |  |  | Medium |  | Development | [6 empty] | Open
BUG-024 |  |  | Medium |  | Development | [6 empty] | Open
BUG-025 |  |  | Medium |  | Development | [6 empty] | Open
BUG-026 |  |  | Medium |  | Development | [6 empty] | Open
BUG-027 |  |  | Medium |  | Development | [6 empty] | Open
BUG-028 |  |  | Medium |  | Development | [6 empty] | Open
BUG-029 |  |  | Medium |  | Development | [6 empty] | Open
BUG-030 |  |  | Medium |  | Development | [6 empty] | Open
BUG-031 |  |  | Medium |  | Development | [6 empty] | Open
BUG-032 |  |  | Medium |  | Development | [6 empty] | Open
BUG-033 |  |  | Medium |  | Development | [6 empty] | Open
BUG-034 |  |  | Medium |  | Development | [6 empty] | Open
BUG-035 |  |  | Medium |  | Development | [6 empty] | Open
BUG-036 |  |  | Medium |  | Development | [6 empty] | Open
BUG-037 |  |  | Medium |  | Development | [6 empty] | Open
BUG-038 |  |  | Medium |  | Development | [6 empty] | Open
BUG-039 |  |  | Medium |  | Development | [6 empty] | Open
BUG-040 |  |  | Medium |  | Development | [6 empty] | Open

## Release Checklist
Production Release Checklist
Complete in order. A failed P0 gate means stop the release until fixed or explicitly approved by the business owner.
Gate ID | Phase | Check | Priority | How to verify | Expected evidence | Owner | Status | Notes / Link
GATE-01 | Source | Fetch remotes; compare main and developement; review all intentional differences | P0 | git fetch --prune; log/diff; review release commit | Commit IDs and approved diff |  | Not Run
GATE-02 | Source | Working tree contains only intended files | P0 | git status plus manual review | Clean or documented status |  | Not Run
GATE-03 | Security | No secrets or unrestricted keys in tracked files/diff | P0 | Secret scan and GitHub alerts | Zero unresolved valid alerts |  | Not Run
GATE-04 | Firebase | Functions build and tests pass on supported Node runtime | P0 | Install/build/test functions | Passing command output |  | Not Run
GATE-05 | Firebase | Cloud Functions and Firestore rules deployed to correct project | P0 | Firebase dashboard/CLI deploy history | Deployment IDs and timestamp |  | Not Run
GATE-06 | Payments | Stripe keys, enable flag, webhook secret, URLs match environment | P0 | Vercel/Firebase/Stripe dashboard review | Configuration screenshots without values |  | Not Run
GATE-07 | Payments | Webhook endpoint is healthy and idempotent | P0 | Send/replay test event | 2xx delivery and one order update |  | Not Run
GATE-08 | Payments | Server rejects client price tampering | P0 | Alter client price and create test session | Stripe charges catalog price |  | Not Run
GATE-09 | Shipping | Maps public-config, referrers, and required APIs are correct | P0 | Check /api/public-config and Google Cloud restrictions | Autocomplete works only on approved hosts |  | Not Run
GATE-10 | Checkout | Mango-only, mixed, and non-mango payment/fulfillment rules pass | P0 | Run PAY-001 through PAY-006 | Screenshots for all three cart types |  | Not Run
GATE-11 | Checkout | Tax, shipping fee, free threshold, and promo math pass | P0 | Boundary tests and Stripe amount comparison | Reconciled totals |  | Not Run
GATE-12 | Catalog | All approved product images and galleries pass Image Audit | P1 | Complete Image Audit sheet | All rows Pass |  | Not Run
GATE-13 | Admin | Price sync does not alter availability; storefront changes reflect | P0 | Run ADM sync/edit/toggle cases | Before/after evidence |  | Not Run
GATE-14 | Mobile | Required iPhone and Android device rows pass | P0 | Complete Device Matrix P0 rows | Screenshots and browser versions |  | Not Run
GATE-15 | SEO | Canonicals, robots, sitemap, noindex, metadata and broken links pass | P1 | Run SEO cases/crawl | Crawler/validator output |  | Not Run
GATE-16 | Quality | All P0/P1 tests pass and no Critical/High defects are open | P0 | Review Dashboard and Defect Log | Dashboard screenshot and approvals |  | Not Run
GATE-17 | Release | Rollback commit/deployment recorded | P1 | Record last known-good main/Vercel deployment | Commit and deployment URL |  | Not Run
GATE-18 | Release | Deploy main and verify Vercel Ready status | P0 | Push approved commit; monitor deployment | Production deployment URL |  | Not Run
GATE-19 | Smoke | Production public smoke passes without a live test charge | P0 | Home, shop, cart, checkout rules, account, policies | Smoke evidence |  | Not Run
GATE-20 | Monitor | Analytics, logs, Stripe webhook, Firebase errors checked after release | P1 | Monitor 30-60 minutes | No unexplained error spike |  | Not Run

## Coverage Guide
Testing Coverage Guide
Recommended execution order, test data, and evidence standards for a practical SHRISH release cycle.
Recommended execution sequence
Phase | Focus | Typical time | Scope | Rule
Phase 1 | Release gates | 20-30 min | REL P0, config, deploy, secrets, webhook, functions/rules | Stop immediately on a P0 failure
Phase 2 | Core business regression | 2-3 hours | Shop, cart, payment rules, shipping, tax, accounts, admin | Use development and Stripe test mode
Phase 3 | Cross-device and accessibility | 1-2 hours | Required Device Matrix rows, keyboard, zoom, mobile safe areas | Capture screenshots for every P0 device
Phase 4 | SEO, performance, and content | 45-90 min | SEO, links, structured data, console, cache, analytics | Record validator/crawl output
Phase 5 | Production smoke | 10-15 min | Home, shop, cart, checkout-rule display, account, legal pages | Do not place an unapproved live charge
Required test data
Data | Recommended setup | Purpose | Cleanup
Customer | Unique QA email alias, valid US phone, non-real name prefixed QA | Account, order claim, email, profile | Delete only if no retained test orders
Products | One mango, one veg pickle, one non-veg pickle, one podi, one unavailable product | Cart rules, filters, images, notify | Restore availability/order after test
Stripe | Official Stripe test cards for success, decline, and 3DS | Payment outcomes and webhook | Keep in test mode; never store card data
Shipping | Valid Virginia address plus one out-of-state US address | Places, tax, shipping fee | Do not use sensitive personal address in evidence
Promos | Percent, fixed, free shipping, expired, minimum, one-use | Promo enforcement | Disable/delete QA promos after test
Admin orders | Manual orders clearly labeled QA | Fulfill, no-show, cancel, reset, print, accounting | Cancel/archive after regression
Evidence standard
Pass | Record test date, tester, environment, and concise evidence for P0/P1 cases.
Fail | Capture full-screen screenshot, exact URL, device/browser, order number, steps, actual result, console/network evidence.
Payment | Record Stripe test session/payment ID and order number. Never paste secret keys or full card data.
Admin | Use before/after screenshots and identify the exact test product/order changed.
Production | Record deployment URL/commit and keep production smoke read-only unless a specific live action is approved.
Reference links
Development site | https://dev.shrish.co/
Production site | https://www.shrish.co/
Stripe test cards | https://docs.stripe.com/testing
Google Places JavaScript | https://developers.google.com/maps/documentation/javascript/place-autocomplete-overview
Google Rich Results | https://search.google.com/test/rich-results
PageSpeed Insights | https://pagespeed.web.dev/